## Sheet1
Date | User Story | Task | Estimate | Time Spent | Task Requirement | Task Description | Status
05-06-2025 | Iteractions | Soft Skill Interaction | 3 | 2 | Rally Board |  | complite
05-06-2025 | Iteractions | Tech Interaction | 5 | 0 | JavaScrip
05-06-2025 | Iteractions | Team interaction | 5 | 0.5 | Presentation |  | complite
06-06-2025 | Project V | React Signup Page Styling | 2.5 | 1.5 | Tailwind CSS |  | complite
07-06-2025 | Project V | Election DB Design Review | 3 | 2 | MySQL |  | complite
10-06-2025 | Project V | React Photo Voting Feature | 4 | 3 | Upload & Shuffle Logic |  | complite
12-06-2025 | Project V | Add Swagger to Backend | 2 | 1 | Swagger/OpenAPI |  | complite
14-06-2025 | Project V | Auth Middleware Implementation | 3 | 2 | JWT/Express |  | complite
16-06-2025 | Project V | Election App Unit Testing | 3.5 | 2.5 | Jest/Supertest |  | complite
18-06-2025 | Project V | Add Liquid Glass Design | 2.5 | 1.5 | Glassmorphism UI |  | complite
20-06-2025 | Project V | Create Infinite Cards Component | 3 | 2 | React Animation |  | complite
22-06-2025 | Project V | 404 Error Page Handling | 2 | 1 | React Routing |  | complite
23-06-2025 | Project V | Meeting Summary on Virtual Teams | 1.5 | 0.5 | Story Writing |  | complite